## Sheet1
Draft Project Plan/Critical Path
[13 empty] | Key: |  | In planning
Agreed/In Action
Delivered/In Place
Launch date
|  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14
Risk/Risk Management |  | VISTOR EXPERIENCE
Risk Documentation
H&S Project overlay
Project Scoping & Overview
Holistic Business risk
Crisis Management plan
Compliance - GDPR/Licencing etc
Commercial Delivery Plan |  | VISITOR EXPERIENCE
Budget/P&L - monthly/seasonality etc
Revenue streams
Footfall/SPH/Conversion rates
Departmental detail
| Ancillary revenue target | Retail
F&B - In-house/Contract?
Photography
Misc - inc partnerships
Building Project & Ongoing |  | VISITOR EXPERIENCE
| Shell | Building
Services
| External | Services
Theming
External F&F
Internal
Services | bar: Month 1 to Month 2
F&F | bar: Month 1 to Month 2
Theming | bar: Month 3 to Month 12; Launch date Month 14
Mechanical | bar: Month 3 to Month 12; Launch date Month 14
Visitor interaction | bar: Month 3 to Month 12; Launch date Month 14
Customer services | bar: Month 3 to Month 12; Launch date Month 14
Facilities Management - Ongoing plan | bar: Month 3 to Month 12; Launch date Month 14
IT Infrastructure |  | VISITOR EXPERIENCE
IT Hardware/Software Scoping
IT Services - internal systems
Ticketing
App
Website
Retail systems
Staff Support/HR systems
Sales & Marketing IT requirements
- Social Media interactions | bar: Month 3 to Month 12; Launch date Month 14
- CRM systems | bar: Month 3 to Month 12; Launch date Month 14
- Sales support docs | bar: Month 3 to Month 12; Launch date Month 14
Attraction Content |  | VISITOR EXPERIENCE
Content detail
Visitor Flow
Opening times/Session times target
Ticketing/web/App/CRM interface
Staff Briefing/Content delivery plan/Ops | bar: Month 4 to Month 12; Launch date Month 14
People |  | VISITOR EXPERIENCE
Organisation structure | bar: Month 1 to Month 2
Vision/Mission/Values => Strategy | bar: Month 1 to Month 2
Comms process
| Recruitment | Senior Leadership | bar: Month 4 to Month 12; Launch date Month 14
Supervisory | bar: Month 8 to Month 12; Launch date Month 14
Team members | bar: Month 9 to Month 12; Launch date Month 14
| Training Project Plan | Leaders | bar: Month 4 to Month 12; Launch date Month 14
Supervisory | bar: Month 4 to Month 12; Launch date Month 14
Team members | bar: Month 4 to Month 12; Launch date Month 14
Operations |  | VISITOR EXPERIENCE
Budget/targets agreed/team ownership | bar: Month 4 to Month 12; Launch date Month 14
Delivery of the Visitor Experience | bar: Month 4 to Month 12; Launch date Month 14
Content Delivery - specific | bar: Month 4 to Month 12; Launch date Month 14
Recruitment | bar: Month 4 to Month 12; Launch date Month 14
Training | bar: Month 4 to Month 12; Launch date Month 14
Rota planning | bar: Month 4 to Month 12; Launch date Month 14
Staffing detail/SOPs/SLAs etc | bar: Month 4 to Month 12; Launch date Month 14
Visitor Experience/Customer Service |  | VISITOR EXPERIENCE
Strategy | bar: Month 6 to Month 12; Launch date Month 14
CRM SOPs | bar: Month 6 to Month 12; Launch date Month 14
CC SOPs | bar: Month 6 to Month 12; Launch date Month 14
CS SOPs | bar: Month 6 to Month 12; Launch date Month 14
Training | bar: Month 6 to Month 12; Launch date Month 14
Social Media interface SOPs/essence | bar: Month 6 to Month 12; Launch date Month 14
Dry Run/soft launch project plan | bar: Month 10 to Month 12
Marketing |  | VISITOR EXPERIENCE
Strategy
Targets
Content
PR
CRM strategy
| Digital Delivery (Web/App/Ticket interface) | All platforms
Sales |  | VISITOR EXPERIENCE
Strategy
Targets
SOPs/SLAs
Training
CRM strategy
S&M interface with Ops